## Ark 1
ID | Depends on | Phases | Tasks | Sub-Tasks | Responsible | Time (weeks) | Notes
P001 |  | Creating the website |  |  |  |  | Writing code and getting everything needed
T001 |  |  | Buying server space |  |  | 2
S001 | T001 |  |  | Finding the best server provider | Fredrik | 1 | Check for the cheapest service
S002 | T001 |  |  | Finding an optimal subscription | Fredrik | 1 | Find out which subscription gets you the most for your money
T002 |  |  | Writing the code |  |  |  | Creating the website
S004 | T002 |  |  | Making navigation | Partner 1 | 0.5 | Making something like a navigation bar so that customers can navigate the site
S005 | T002 |  |  | Making menu | Partner 1 | 2 | Setting up the menu so that customers can view products
S006 | T002 |  |  | Making order page | Partner 2 | 1 | So that customers can place order
S007 | T002 |  |  | Writing down the company address | Partner 2 | 0.5 | Providing customers with address if they want to visit the physical store
S008 | T002 |  |  | Making login and register page | Partner 3 | 0.5 | Allowing customers to make an account so that they can get benefits
S009 | T002 |  |  | Making a place to store customers passwords and purchase info | Partner 4 | 2 | Server space that will store customer login info etc.
T003 |  |  | Designing website |  |  |  | Designing the website
S010 | T002 |  |  | Finding pictures | Fredrik | 3 | Finding/taking pictures of products
S011 | T002 |  |  | Writing CSS code | Partner 2 | 2.5 | Using CSS to design the website
S012 | T002 |  |  | Making/implementing logo | Partner 4 | 2 | Putting the company's logo onto the website
S013 | T002 |  |  | Finding colors | Partner 4 | 2 | Finding the colorway to be used for the website
P002 |  | Product prices |  |  |  |  | Deciding optimal product prizes
S014 |  |  | Finding price that allows for maximum profit |  | Partner 1 | 1 | Finding the best prices to get the most sales possible
S015 |  |  | Finding out optimal shipping costs |  | Partner 1 | 1 | Finding the best shipping prices that will get the most sales
P003 | P002 | Package tracking/customer service |  |  |  |  | Making a tracking option available
T004 | P002 |  | Partnering with shipping companies for package tracking |  | Partner 3 | 2 | Finding a shipping company that will allow package tracking
T005 | P002 |  | Providing customers with a phone number and creating a chat option on the website |  | Fredrik | 1.5 | Make sure that customer can call/chat with an employee if they have any concerns